## Plan
Plan
Requirement (ID) | Task ID | Task | Start (date) | End (date) | Estimate (days) | Who |  | Status | Remaining Work | Dependencies
Create responsive index page (R006, R017) | T1 | Coding HTML | 2017-04-04 | 2017-04-10 | 7 | Iva | Kipras | Pending
| T2 | Coding CSS | 2017-04-04 | 2017-04-10 | 7 | Iva | Renata | Pending
Creating HTML form sign in | T3 | Coding | 2017-04-04 | 2017-04-07 | 4 | Kipras | Mihael | Pending
Interface for creating questions (R001, R002, R008, R011, R014, R015) | T4 | Coding HTML | 2017-04-12 | 2017-04-14 | 3 | Mihael | Kipras | Pending
| T5 | Coding CSS | 2017-04-12 | 2017-04-14 | 3 | Mihael | Kipras | Pending
| T6 | Coding PHP | ? | ? |  | Renata | Mihael | Pending
Interface for answering questions (R003, R009, R012) | T7 | Coding HTML | 2017-04-14 | 2017-04-16 | 3 | Tena | Mihael | Pending
| T8 | Coding CSS | 2017-04-14 | 2017-04-16 | 3 | Tena | Iva | Pending
| T9 | Coding PHP | ? | ? |  | Renata |  | Pending
| T10 | Database | 2017-05-03 | 2017-05-03 | 1 | Tena | Kipras | Pending
Creating a database | T11 | Analyzing and categorizing data | 2017-04-21 | 2017-04-22 | 2 | Tena | Iva | Pending
| T12 | Creating tables and relationships | 2017-04-23 | 2017-04-30 | 8 | Tena | Iva | Pending
Entering Data | T13 | Coding PHP to connect to the database | TBD | TBD |  | Renata | Tena | Pending
Analyzing data (R004) | T14 | TBD | [5 empty] | Pending
| T15 | TBD | [5 empty] | Pending
| T16 | TBD | [5 empty] | Pending
Showing results (R007, R010, R013, R016) | T17 | Coding PHP | ? | ? |  | Renata | Mihael | Pending
Limiting users (R005) | T18 | Coding XML | ? | ? |  |  |  | Pending
Total Estimate & Remaining: |  |  |  |  | 41

## Dijagram - aktivnosti
Task ID | Start Date | End Date | Duration
T1 | 2017-04-04 | 2017-04-10 | 7
T2 | 2017-04-04 | 2017-04-10 | 7
T3 | 2017-04-04 | 2017-04-07 | 4
T4 | 2017-04-12 | 2017-04-14 | 3
T5 | 2017-04-12 | 2017-04-14 | 3
T6 | TBD | TBD
T7 | 2017-04-14 | 2017-04-16 | 3
T8 | 2017-04-14 | 2017-04-16 | 3
T9 | TBD | TBD
T10 | 2017-05-03 | 2017-05-03 | 1
T11 | 2017-04-21 | 2017-04-22 | 2
T12 | 2017-04-23 | 2017-04-30 | 8
T13 | TBD | TBD
T14 | TBD | TBD
T15 | TBD | TBD
T16 | TBD | TBD
T17 | TBD | TBD
T18 | TBD | TBD
T1(M1)
T1, T2(M2)
T1, T2, T3(M3)
T4(M4)
T1(M5)
T7(M6)
T9(M7)
T10(M8)
T10, T11(M9)